## Sheet1
Sl | Resource | Task | Timeline | Status
1 | Account Setup | Go through below link and create free tier aws account. https://docs.aws.amazon.com/awsconsolehelpdocs/latest/gsg/getting-started.html . https://docs.aws.amazon.com/awsaccountbilling/latest/aboutv2/tracking-free-tier-usage.html https://docs.aws.amazon.com/awsaccountbilling/latest/aboutv2/billing-free-tier.html. Use only Free tier Services for learning and keep track of billing by setting alerts. Get Familiar with different Services like IAM,S3,Lambda, Athena,Dynamodb,SNS,SQS,Glue | 2020-07-24 | 75%
2 | Git Project | Create Git project for Each Week , add code, aws screenshot , details and comments and share the link for evaluation | 2020-07-24 | 50%
3 | Terraform | Install Terraform and link aws account with local terraform. Below link will help to do that. https://hackernoon.com/introduction-to-aws-with-terraform-7a8daf261dc0. https://blog.gruntwork.io/an-introduction-to-terraform-f17df9c6d180?gi=6dff7f676654 | 2020-07-24
4 | IAM | Use Terraform to create Iam policy + role + having access to s3 and cloudwatch | 2020-07-24
5 | S3 | Create S3 and upload any file to S3 | 2020-07-24
6 | Boto3 | Learn about boto3 library and Different function available for working with dynamodb,lambda,glue | 2020-07-31
7 | Glue | Get Familiar with Boto3 library. Use glue job to read text/csv file from s3 and log the content into cloudwatch | 2020-07-31
8 | Athena | Read data from csv file in s3 using athena with glue catalog | 2020-07-31
9 | DynamoDB | create dynomodb table, learn about getitem, putitem function of boto3 | 2020-07-31
10 | Lambda | a. Connect to AWS glue from Lambda and pass a variable as an input argument to glue via lambda. | 2020-07-31
b. Read dynamodb data via Lambda and print item in Lambda response.
c. Create a lambda script to read current date and change the format to DD/MM/YYYY and display in lambda response.